## Sheet1
ID | Issue Type | Severity | Platform | Description | Testing results | Comments
1 | Bug | Minor | Mobile | 1st button should read “Pre-Start Inspection” not “Daily Inspection” | Reproduced
2 | Bug | Minor | Web | Cropping signature works fine, but doesn’t show correctly on output PDF | Reproduced
3 | Bug | Minor | Mobile/Web | Critical header text should be: “Critical Alerts” and be centred. | Reproduced
4 | Bug | Major | Mobile | Do pending inspections attempt to resubmit automatically? I have had one sitting there for 24 hours and no change. | Reproduced
5 | Bug | Minor | Mobile | Predictive text does not show Plant ID when beginning to type. | Reproduced
6 | Bug | Minor | Mobile | Heading should be “Pre-Start Inspection” not “Daily Inspection Checklist” (same for all successive screens). | Reproduced
7 | Bug | Minor | Mobile | Auto-fill not working for database system. | Reproduced
8 | Bug | Minor | Mobile | Order of fields feels jumbled. Fields should be in the following order: - Project Name - Project Number - Operator’s Name - Plant ID - Vehicle Make - Vehicle Model - Next Service Due - Current Odometer - Vehicle Location - GPS toggle | Reproduced
9 | Bug | Major | Mobile | What does “Kilometres/Hours value is too big” error message mean? Is this the confirmation of accuracy if data input is Kms > 500 or Hours > 24? Cannot bypass this error when editing a pending inspection. | Reproduced
10 | Bug | Minor | Mobile | Where is the Registration expiry field? | Cannot reproduced | Is displayed under the GPS toggle
11 | Bug | Minor | Mobile | Enabling GPS for the email system is not necessary if there is no map or coordinates generated on the output PDF. | Reproduced
12 | Bug | Minor | Mobile/Web | Vehicle Stability does not need to be recorded as an alert or in the database/output PDF. | Not a bug | Depends on the checklist settings
13 | Bug | Minor | Mobile | “N/A” option on checklist has now disappeared? | Reproduced
14 | Bug | Minor | Mobile | “Radio buttons should not be blank” error message – please change to “Please fill in all required fields.” | Reproduced
15 | Bug | Minor | Mobile | Do not show alert pop-up dialog boxes on this screen | Not a bug | Depends on the checklist settings
16 | Bug | Normal | Mobile | Alerts list does not show name of alerts (critical and non-critical) | Reproduced
17 | Bug | Minor | Mobile | Space for additional comments and photos should have a “+” button to expand if user chooses to add comments/photos. It should not be open by default as it gets very long to scroll with multiple alerts, and you cannot see a list of alerts in one screen. | Reproduced
18 | Bug | Minor | Mobile | Sometimes get error “The uploaded file does not reach the min allowed size”. It takes me to Stored Docs page where I then have to submit manually. | Cannot reproduced
19 | Bug | Minor | Mobile | Q4 – “Are tyres correctly inflated…” A NO answer should not trigger a critical alert | Not a bug | Depends on the checklist settings
20 | Bug | Minor | Mobile | Q5 – “Are you authorized to inflate/change tyres…” should only show if Q4 was answered with a NO. | Not a bug | Depends on the checklist settings
21 | Bug | Minor | Mobile | Hours field should only allow for numeric characters to be entered (not letters). | Reproduced
22 | Bug | Minor | Mobile | Dialog box pop up for Q1 “Do not continue if ground conditions are not suitable” should be coloured red, and have the word “DANGER” above the message. | Not a bug | Depends on the checklist settings
23 | Bug | Minor | Mobile | Q3-9, answer NO should not have red popups (or any popups at all). | Reproduced
24 | Bug | Minor | Web | Additional Checklist Page – Please include the text: “Do you need to perform additional inspections for any of the following equipment?” (so it is the same as the app) | Reproduced
25 | Bug | Minor | Web | Trailer checklist – same as app, the tyre question (Q7) should only show if someone selects NO for Q4 (and selecting NO should not trigger a Critical Alert). | Not a bug | Depends on the checklist settings
26 | Bug | Normal | Mobile | Review screen – checklists names should link back to the respective pages in case the user wants to make changes (should not have to press Back multiple times to get to page) | Reproduced
27 | Bug | Minor | Web | Review screen - the alerts should have a heading “Critical Alerts” and “Non-Critical Alerts” similar to the app | Reproduced
28 | Bug | Minor | Web | Vehicles -> Current Information – Not all vehicles require data entry for Next Service Due (Hours). If this is entered as 0, it defaults to 24 when trying to save the info. This should not be the case (since it will not use hours in its reporting). | Reproduced | ToDo QA
29 | Bug | Minor | Web | Vehicles -> Previous Inspections – Submitting an edited inspection (via Previous Inspections page) does not seem to work. Clicking Confirm does not seem to submit the inspection, and the changes are not saved. | Reproduced | ToDo QA
30 | Bug | Minor | Web | Vehicles - Error when printing action list without access: {"meta":{"status":200,"errorCode":204},"data":{"errorMessage":"No vehicles available for getting Action List"}} Can we have a more user-friendly error message? Maybe a popup instead? | Reproduced | ToDo QA
31 | Bug | Normal | Web | Vehicles - Deleted vehicles still show in vehicle list in sidebar after deleting them. | Reproduced
32 | Bug | Minor | Web | Vehicles -> Manage Checklists – When adding a new checklist item, Alert Critical should be OFF by default, and “N/A” option should show in drop down list (currently only shows <Blank> ¦ Yes ¦ No) | Reproduced
33 | Bug | Minor | Web | Alerts – what does search function do? It does not search by plant ID, vehicle make/model or Alert name. | Reproduced
34 | Bug | Minor | Web | Users – a bug was noticed when trying to edit Users on one occasion. No user info showed, and when clicking on user name the users in the sidebar follow the mouse up and down as if they are being dragged. | Cannot reproduced
35 | Bug | Minor | Web | Settings – Company logo needs to be visible (currently is a cropped square) | Reproduced
36 | Bug | Minor | Web | Settings – Change company logo button does not look very polished. The text is too high, and the button is not wide enough for the text. | Reproduced
37 | Bug | Minor | Web | When logging in as different user on same device, navigating to Change Password dialog box shows the previous users credentials. | Cannot reproduced
38 | Bug | Minor | Web | SUPER ADMIN -> Statistics – Where is usage breakdown for each company? | Not a bug | http://clip2net.com/s/6aiTQM
39 | Bug | Minor | Web | Project Numbers do not show on Output PDF | Cannot reproduced
40 | Bug | Minor | Web | Any negative values should have red text NO instead of ALERT. | Reproduced
41 | Bug | Minor | Mobile/Web | Date of fire extinguisher is incorrect (ensure it is in format DD/MM/YYYY) | Reproduced
42 | Bug | Minor | Web | Vehicle Stability in Safety checklist and Isolation, Remove Isolation fields in Mechanical checklist do not need to be on Output PDF, please remove. | Reproduced
43 | Bug | Minor | Web | Uploaded company logo does not fit (is cropped to a square) and logo’s with transparency layers (PNG files) show with a black background instead of a white one. | Reproduced
44 | Bug | Minor | Mobile/Web | Non-critical errors (without specific dialog boxes) still show blank dialog box when clicked in the app. | Reproduced
45 | Bug | Minor | Mobile | Dialog boxes in app could be smaller and more rectangular (they look very big and bulky now, before they looked good) | Reproduced
46 | Bug | Minor | Mobile/Web | Dates across entire system should be in DD/MM/YYYY format. | Reproduced
47 | Bug | Minor | Web | Reporting dates sometime show incorrectly (system date seems to start at year 1970, Fire extinguisher expiry date on output PDF is 1/1/1970). | Reproduced
48 | Bug | Minor | Mobile/Web | Push Notifications are not being received for alerts. | Reproduced | The functional works, the server was changed, so the app settings should be changed.
49 | Bug | Minor | Web | Where are our HTML email templates? | Not a bug | We are expecting the final version
50 | Bug | Minor | Mobile | Plant IDs are NOT case-sensitive – this causes problems when using the app, it senses that the plant ID does not exist in the system (when it is just wrong case). | Reproduced
|  | ID | Issue Type | Description | Comments | Estimation
|  | 1 | CR | Vehicles -> Alerts - Current outstanding Alerts number in Vehicles sidebar does not reduce when an Alert is marked as completed or deleted. |  | 2
|  | 2 | CR | Vehicles -> Manage Checklists – When adding a new checklist item, the position value should have a max limit depending on number of existing checklist items (ie. If there are only 10 items, when creating a new item the position should not be able to go over 11). | The logic should be clarified | 4
|  | 3 | CR | Alerts – Alerts tab badge showing number of outstanding alerts does not reduce immediately when alerts are deleted or completed. | The logic should be clarified | 2
|  | 4 | CR | Can we have a “Home” button that links to the main app screen from this page? It saves users having to pass through the inspection to get back to the main screen.
|  | 5 | CR | Inspection -> Mechanical – Remove Isolation field needs to be removed. | The logic should be clarified | 0 (Depends on the checklist settings)
|  | 6 | CR | Reporting Page – can we have a bar graph instead of line graph as specified in the documentation? |  | 6
|  | 7 | CR | Reporting – Monthly/Weekly reports need to show the specific alerts that were raised in the chosen period and on what dates. | Additional statistics | 6
|  | 8 | CR | Action list – where is the functionality to email directly to the vehicle’s Reponsible person? | it was discussed that there is no need to implement | 2
|  | 9 | CR | If no hours are entered, it is not necessary to show them on the output PDF (next to KMs) |  | 1
|  | 10 | CR | Vehicles - When the subscription manager creates a vehicle in the database, he should automatically have access rights to that vehicle, not “No Access”. There should not be an option to change access rights for subscription manager anyway since he has access to ALL vehicles by default. | The logic should be clarified | 4