## CR
ID | Issue Type | Description | Comments | Estimation
1 | CR | Vehicles -> Alerts - Current outstanding Alerts number in Vehicles sidebar does not reduce when an Alert is marked as completed or deleted. | The status updates once in 5 seconds. | 2 | Approved
2 | CR | Vehicles -> Manage Checklists – When adding a new checklist item, the position value should have a max limit depending on number of existing checklist items (ie. If there are only 10 items, when creating a new item the position should not be able to go over 11). | Currently it works, new sorting method requiries additional work | 4 | Declined
3 | CR | Alerts – Alerts tab badge showing number of outstanding alerts does not reduce immediately when alerts are deleted or completed. | The status updates once in 5 seconds. | 2 | Approved
4 | CR | Can we have a “Home” button that links to the main app screen from this page? It saves users having to pass through the inspection to get back to the main screen. |  | 1 | Approved
5 | CR | Reporting Page – can we have a bar graph instead of line graph as specified in the documentation? | It's written in the specification "bar/line graph", not just "bar graph". | 6 | Declined
6 | CR | Reporting – Monthly/Weekly reports need to show the specific alerts that were raised in the chosen period and on what dates. | Additional statistics | 6 | not a CR
7 | CR | Action list – where is the functionality to email directly to the vehicle’s Reponsible person? | It was discussed that there is no need to implement. We will do that as a task (not CR) with the lowest priority. | 2 | done (not a CR)
8 | CR | If no hours are entered, it is not necessary to show them on the output PDF (next to KMs) |  | 1 | Approved
9 | CR | Vehicles - When the subscription manager creates a vehicle in the database, he should automatically have access rights to that vehicle, not “No Access”. There should not be an option to change access rights for subscription manager anyway since he has access to ALL vehicles by default. |  | 4 | Declined
11 | CR | Hours field should only allow for numeric characters to be entered (not letters). | We need to make a new field (numeric text field), and adding a new field requires 12 hours (work of iOS + Android + Web developers). | 12 | Declined
12 | CR | Submitted inspections should be viewable offline (not in google docs pdf). This has changed since beta version |  | Show submitted inspections in the applications (not as a PDF) Android 6h, iOS 6h | no decision yet
13 | CR | Need to show Plant IDs on FR_005 dropdown, not Vehicle Make |  | Move Vehicle Make and put it on FR_006. Leave Plant ID as it is on FR_005. This is more in line with what we have in the specification. Android: 4h, iOS 4h | no decision yet
14 | CR | Is it possible to have tablet app forced to landscape mode? Portrait mode feels cramped and the sidebar line does not match up with the logo line. |  | If you mean only database-webview to be in the landscape mode, it will take Android: 1h, iOS: 1h | Approved
15 | CR | Data value for hours field should be able to go to one decimal place. Therefore we need a period button for the keyboard |  | iOS: 4h, Android: 4h | Declined
16 | CR | Also, is it possible to have on the Web database, on Vehicles screen, where it says Previous Inspections (X) can we have Previous Inspections (X Days Since Last) instead |  | Web: 4h | Approved